TOP PERFORMER COACH

Go-To-Market Campaign Plan

"Unleash Your Potential" Launch Campaign

February 2026  |  Prepared for Mike Perkins

Phase 1: Free Launch & Community Building

# 1. Campaign Overview

Campaign Name: "Unleash Your Potential" - Top Performer Coach Launch

Summary: Drive organic downloads and build an engaged community of ambitious professionals, fitness enthusiasts, and students through social media virality, influencer partnerships, and a user-generated content strategy that turns early adopters into brand ambassadors.

Primary Objective: 10,000 downloads in first 90 days with 30% Day-7 retention

Secondary Objectives: Build email list of 5,000+, achieve 4.5+ App Store rating, create foundation for viral contest at official launch

Timeline: 12-week rolling campaign starting at App Store approval

Budget: Lean/bootstrap - prioritizing $0 organic channels with optional paid amplification

# 2. Target Audience

## Primary Segments (ROI-Ranked)

Segment A: Salespeople & Outgoing Professionals

High-energy, goal-driven individuals in sales, business development, and entrepreneurship. They already track quotas and KPIs - Top Performer Coach gives them a system to track the habits behind their numbers. They're vocal on LinkedIn and Instagram, love sharing wins, and naturally become brand ambassadors.

Where they are: LinkedIn, Instagram, X/Twitter, sales podcasts, Clubhouse rooms

Pain points: Inconsistent performance, burnout cycles, no system for personal development beyond work metrics

Viral potential: VERY HIGH - they love public accountability and celebrating wins

Segment B: Up-and-Coming Health & Fitness Influencers

Micro-influencers (1K-50K followers) in wellness, fitness, and self-improvement who are building their own brands. They need content ideas and authentic partnerships. Top Performer Coach becomes part of their daily routine content.

Where they are: TikTok, Instagram Reels, YouTube Shorts, fitness communities

Pain points: Need fresh content angles, want to differentiate from other fitness creators

Viral potential: EXTREMELY HIGH - they create content daily and their audiences trust their recommendations

Segment C: Sorority & Greek Life Communities

Sorority members are hyper-connected, brand-loyal, and socially active. They share everything with their chapters and have built-in distribution networks across campuses nationwide. A single adoption by chapter leadership can mean 50-200 downloads overnight.

Where they are: Instagram, TikTok, GroupMe, chapter meetings, campus events

Pain points: Academic-social balance, wellness accountability, wanting to stand out professionally post-graduation

Viral potential: EXTREMELY HIGH - built-in sharing networks, competitive culture, social proof driven

How to reach them: Partner with Panhellenic councils, sponsor sisterhood events, recruit chapter wellness chairs as ambassadors, connect through campus wellness programs and Greek life Instagram pages

Segment D: Broad Self-Improvement Seekers

Students, early-career professionals, and anyone actively investing in personal growth. They consume self-help content, follow productivity influencers, and are looking for a practical tool to turn inspiration into action.

Where they are: Reddit (r/selfimprovement, r/getdisciplined), YouTube, podcasts, TikTok

Pain points: Information overload, can't stick to habits, want AI-personalized guidance

# 3. Key Messages

Core Message: "Top Performer Coach is the AI-powered habit system that adapts to YOUR style - not a one-size-fits-all approach."

## Supporting Messages by Audience

| Audience | Message | Proof Point |
| --- | --- | --- |
| Salespeople | Track the habits behind your numbers. Your quota has a formula - we help you find it. | AI coaching adapts to your energy, schedule, and goals in real-time |
| Health Influencers | Show your audience the full picture. Fitness is just one piece - track all your growth. | Shareable progress dashboards and streak visualizations for content |
| Sororities | Level up together. Track goals as a chapter and hold each other accountable. | Personal coaching that balances academics, wellness, social life, and career prep |
| Self-Improvement | Stop reading about habits. Start building them with AI that knows you. | Personalized daily coaching vs generic habit trackers |

# 4. Channel Strategy (ROI-Ranked)

Channels ranked by estimated ROI considering cost, automation potential, and impact for a bootstrapped launch:

| # | Channel | Cost | Effort | ROI | Automate? | Why |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | App Store Optimization | $0 | Medium | HIGHEST | Set & refine | 65% of downloads come from search. One-time setup with ongoing tweaks. |
| 2 | TikTok/Reels | $0 | High | VERY HIGH | Batch create | Viral potential is unmatched. One hit = thousands of downloads overnight. |
| 3 | Influencer Seeding | $0-500 | Medium | HIGH | Templated outreach | Micro-influencers often post for free product access. Authentic > paid. |
| 4 | Sorority/Campus | $0-200 | Medium | HIGH | Ambassador program | Built-in networks. One chapter = 50-200 downloads. Scales with each campus. |
| 5 | LinkedIn Organic | $0 | Medium | HIGH | Schedule posts | Salespeople live here. Thought leadership + app mention = qualified downloads. |
| 6 | Referral Program | $0 | Low (in-app) | HIGH | Fully automated | Users invite users. Compound growth. Can tie into contest mechanics. |
| 7 | Email/Newsletter | $0-50/mo | Low | MEDIUM | Fully automated | Nurture signups, announce features, drive re-engagement. Drip sequences work while you sleep. |
| 8 | Reddit/Communities | $0 | Medium | MEDIUM | No (authentic only) | r/selfimprovement, r/sales, r/getdisciplined. Must add value, not spam. |
| 9 | Landing Page | $0-20/mo | One-time | MEDIUM | Set & forget | SEO long game + email capture + social proof hub. Foundation for everything else. |
| 10 | Apple Search Ads | $5-20/day | Low | MEDIUM | Fully automated | 60%+ conversion rate. Best paid channel for apps. Start small, scale what works. |

# 5. Content Calendar (12-Week Rollout)

## Phase 1: Launch Week (Weeks 1-2)

| Day | Content | Channel | Notes |
| --- | --- | --- | --- |
| Day 1 | Launch announcement post + App Store link | All social | Personal accounts first for authenticity |
| Day 2 | "Why I built this" story video (60-90 sec) | TikTok, Reels, LinkedIn | Founder story drives connection. Be real. |
| Day 3 | First influencer posts go live | Instagram, TikTok | Coordinate with 3-5 micro-influencers |
| Day 4 | App walkthrough / demo video | YouTube, TikTok | Show the AI coaching in action |
| Day 5 | User testimonial (early beta feedback) | Instagram Stories, LinkedIn | Social proof from TestFlight users |
| Days 6-7 | Reddit posts in r/selfimprovement, r/productivity | Reddit | Value-first: share insights, mention app naturally |
| Week 2 | Daily social content + email welcome sequence live + ASO refinement | All channels | Analyze Day 1-7 data, double down on what works |

## Phase 2: Community Building (Weeks 3-6)

| Week | Content Focus | Channel | Goal |
| --- | --- | --- | --- |
| Week 3 | "7-Day Challenge" launch - daily habit challenge with app | TikTok, Instagram | Drive engagement + UGC with #TopPerformerChallenge |
| Week 4 | Sorority outreach begins - wellness chair partnerships | Instagram DMs, email | Secure 5-10 chapter ambassadors |
| Week 5 | Sales performance content series - "Habits of Top Closers" | LinkedIn, X/Twitter | Attract salespeople with value-first content |
| Week 6 | First monthly recap + user spotlight features | All channels, email | Social proof + retention push + review requests |

## Phase 3: Scale & Contest Prep (Weeks 7-12)

| Week | Content Focus | Channel | Goal |
| --- | --- | --- | --- |
| Weeks 7-8 | Double down on top-performing content formats + expand influencer roster | Best-performing channels | Optimize based on data from Weeks 1-6 |
| Weeks 9-10 | Pre-contest hype - tease the upcoming challenge/giveaway | All channels | Build anticipation, grow email list for contest launch |
| Weeks 11-12 | CONTEST LAUNCH (see Section 8) + paid amplification if budget allows | All channels + paid | Viral spike targeting 5,000+ downloads in 2 weeks |

# 6. Influencer & Ambassador Strategy

## Micro-Influencer Playbook

Target up-and-coming health, fitness, and self-improvement influencers with 1K-50K followers. They're more authentic, more affordable (often free), and their audiences are highly engaged.

Outreach Template

"Hey [Name], I love your content about [specific topic]. We just launched Top Performer Coach - an AI-powered habit coaching app. I think your audience would genuinely benefit from it. Would you be open to trying it free and sharing your honest experience? No strings attached."

What We Offer Influencers

- Free premium access for life

- Custom referral code for their audience to track impact

- Feature on our social channels (cross-promotion)

- Early access to new features

- Revenue share / affiliate commission when premium launches

## Sorority Ambassador Program

Recruit 1-2 ambassadors per chapter (target wellness chairs, VP of standards, or social chairs). They introduce the app at chapter meetings and create accountability groups within the sisterhood.

How to Reach Sorority Chapters

- DM sorority chapter Instagram accounts directly with a tailored pitch

- Contact Panhellenic councils at target universities about wellness programming

- Sponsor sisterhood/wellness events (low cost: branded stickers, premium access codes)

- Partner with campus wellness centers who can recommend the app

- Run inter-chapter challenges (chapter with most streaks wins a prize)

- Create "Greek Life" content angle - "How Top Sorority Women Build Winning Habits"

# 7. App Store Optimization Strategy

65% of App Store downloads come from search. This is the highest-ROI channel and should be perfected before anything else.

Keyword Targets

- Primary: "habit tracker", "AI coach", "personal development", "daily habits"

- Secondary: "goal tracker", "self improvement", "performance coach", "habit coach"

- Long-tail: "AI habit coaching app", "personalized habit tracker", "daily routine planner"

ASO Action Items

- Optimize subtitle and keyword field with top-searched terms

- A/B test screenshots (feature-focused vs lifestyle-focused)

- Add app preview video showing AI coaching in action

- Prompt for ratings after positive interactions (Day 3-5 in-app)

- Update keywords monthly based on App Store Connect analytics

# 8. Contest Concept: "30-Day Top Performer Challenge"

Designed for the official release or once a strong free user base is established. This is the viral engine.

## Contest Structure

Duration: 30 days

Mechanic: Users compete to build the longest streak and highest performance scores in the app. Share daily progress on social media with #TopPerformerChallenge for bonus entries.

Entry: Download the app (free) + opt in via email

Prize Tiers

| Tier | Prize | How to Win |
| --- | --- | --- |
| Grand Prize (1) | $500 cash + 1 year premium + featured on all channels | Highest overall score (streaks + engagement + referrals) |
| Runner Up (5) | $100 gift card + 6 months premium | Top 5 overall scores |
| Viral Star (1) | $250 cash + lifetime premium | Most creative/viral social post about the app |
| Referral King (1) | $250 cash + lifetime premium | Most successful referrals |
| Chapter Champ (1) | Pizza party + premium for entire chapter | Sorority/frat chapter with most active members |
| Everyone (all) | Exclusive badge + 1 month premium free | Complete the 30-day challenge |

## Viral Mechanics

- Referral bonus entries: Each friend who joins = 5 extra points

- Daily social sharing: Post progress screenshot with hashtag = 1 bonus entry/day

- Leaderboard: Public rankings drive competition (salespeople LOVE this)

- Team/chapter mode: Groups compete against each other for bragging rights

- Influencer amplification: Partners promote the challenge to their audiences

Estimated Contest Budget

Total: ~$1,500-2,500 (prizes + minor promotion costs). Expected return: 5,000-15,000 downloads if viral mechanics work. Cost per download: $0.10-0.50 (vs $2-5 industry average for paid installs).

Recommended Contest Tools

SweepWidget (free plan available), Gleam (free tier), or Viral Loops for referral tracking. All integrate with email and social platforms.

# 9. Success Metrics & KPIs

| KPI | 90-Day Target | Tracking Method | Cadence |
| --- | --- | --- | --- |
| Total Downloads | 10,000 | App Store Connect Analytics | Daily |
| Day-7 Retention | 30%+ | Firebase/Mixpanel | Weekly |
| App Store Rating | 4.5+ stars | App Store Connect | Weekly |
| Email List Size | 5,000 subscribers | Email platform (Mailchimp/Beehiiv) | Weekly |
| Social Followers | 2,500 combined | Platform analytics | Weekly |
| Influencer Partners | 20 active | CRM/spreadsheet | Monthly |
| Referral Rate | 15% of users refer 1+ | In-app referral tracking | Weekly |
| Sorority Chapters | 10 active chapters | Ambassador tracking | Monthly |

# 10. Risks & Mitigations

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Low initial downloads | Medium | Diversify channels early. Don't rely on one. Have 3-5 influencers queued for launch week. |
| Poor retention | Medium | Monitor Day-1 and Day-7 retention daily. Ship UX improvements fast. Push notifications for re-engagement. |
| App Store rejection / delays | Low | Already submitted. Have TestFlight ready as backup distribution channel for beta users. |
| Negative reviews early on | Medium | Respond to every review. Fix reported bugs within 48 hours. Ask happy users to rate. |
| Contest doesn't go viral | Medium | Seed with influencer participation. Have 500+ users before launching contest. Set realistic floor expectations. |

# 11. Immediate Next Steps

Actions to take THIS WEEK while the app is in review:

- Set up social media accounts (Instagram, TikTok, LinkedIn, X) with consistent branding

- Build landing page with email capture (Carrd.co, Framer, or custom)

- Draft first 10 social media posts (batch create for launch week)

- Identify and DM 20 micro-influencers in health/fitness/self-improvement

- Research target sorority chapters at 5-10 universities near you

- Set up email marketing (Beehiiv free tier or Mailchimp) with welcome sequence

- Record your founder story video for launch day

- Set up App Store Connect analytics and daily review monitoring

Ready to start executing. Let's make Top Performer Coach go viral.